## Slide 1
MID WALES JOINT COMMITTEE FOR HEALTH AND CARE
Autumn Meeting - 14th November 2023
Bronglais District General Hospital Strategy:
Delivering Excellent Rural Acute Care
Progress on implementation of strategy
Peter Skitt
County Director Ceredigion, Hywel Dda University Health Board / Programme Director, Mid Wales Joint Committee

## Slide 2
Introduction
“Bronglais General Hospital: Delivering Excellent Rural Acute Care” approved by the Hywel Dda UHB Board 28th November 2019.
Bronglais General Hospital Steering Group established May 2021.
BGH Strategy Implementation Plan developed May 2021 focusing on Acute Medicine, Scheduled Care, Theatres, Laboratory Services, Pharmacy Services, Use of BGH Estates, Paediatric Services, Radiology Services, Acute Frailty Team, Same Day Emergency Care (SDEC), Therapies and Digital Strategy for Bronglais.
Progress towards delivery of the Strategy has been made in many areas despite the challenges of the COVID-19 pandemic and NHS financial position.

## Slide 3
  Second Respiratory Consultant
    Looking to 'Grow your Own' within Bronglais General Hospital SAS team. One doctor from the Bronglais SAS team has gone to work at Glangwili Hospital, Carmarthen alongside the Respiratory Consultant for 12 months and will after this time period return to Bronglais Hospital.
    On-going advertisement for Respiratory Consultant
  Appointment of Consultant Rheumatologist who commenced in post in October 2023.
  Second Gastroenterology Consultant in place
  Bronglais General Hospital Recruitment Campaign
    Video tour produced
Acute Medicine

## Slide 4
  Appointment made to the following posts:
    Diabetes Band 6 and Band 7
    Cardiology Advanced Nurse Practitioner
    Stroke Advanced Nurse Practitioner and Stroke Clinical Nurse Specialist
    Parkinson's Advanced Nurse Practitioner
    Inflammatory Bowel Disease Clinical Nurse Specialist
    Alcohol Liaison Nurse
    Blood-Borne Virus Clinical Nurse Specialist
  For the Advanced Nurse Practitioner Diabetic Service a Health Board wide appointment has been made to a Band 8A post.
Nursing

## Slide 5
Theatres
Recruitment is progressing to the current funded establishment for Theatres at Bronglais General Hospital.
Current funded commitment:
  NCEPOD x 10, Elective x 20 Cardiology x 1 = 31
Current actual:
  NCEPOD x 10, Elective x 19 Cardiology x 1 = 30

## Slide 6
New skill-mix now in place to maximise flexibility and efficiency.
Career pathway for Band 2/3 Laboratory Assistants developed to progress to Assistant Practitioner and Biomedical Scientist roles.
Plan developed to optimise Phlebotomy provision across 7 days with weekend mornings now part of contracted hours.
Laboratory Services

## Slide 7
Medicines Transcribing and e-Discharge System (MTeD) - MTeD established and now being used in the Clinical Decision Unit.
7 day service - Extended pharmacy service provided to the Emergency Department Monday to Friday. In the process of recruiting to establish a Saturday service. Will evaluate Saturday service after 6 months before taking decision on introducing a Sunday service.
Pharmacy robot - New robot in place and functioning at the Pharmacy department, Bronglais General Hospital.
Pharmacy Services

## Slide 8
Immediate short term action is to stabilise staffing levels on Paediatric ward at Bronglais General Hospital.
Running alongside this work will be undertaken on building relationships with Aberystwyth University in terms of providing placements for students and exploring the development of a dedicated Paediatrics course at the Aberystwyth School of Nursing.
Once staffing levels are the medium / long term plan for the development of a Rural Paediatric Unit will be progressed which will include rotational nursing models with the ED department, development of community Paediatrics outreach/acute response nursing team, exploring opportunities for joint working/recruitment in relation to the Aberystwyth Wellness Centre and single point of contact for Paediatric advice.
Paediatric Services

## Slide 9
Radiology Procedure Room in place and operational
New CT Scanner in place and operational
Digital xray rooms in place and operational
Further works on-going in renewing existing digital infrastructure
Radiology Services

## Slide 10
Acute Frailty Working Group established.
Acute Frailty Team in place and operational.
Bronglais General Hospital and Ceredigion Frailty Forum established.
Network of Frailty Champions across Bronglais General Hospital established, training sessions for the Champions have commenced and will continue.
Frailty Working Group has defined the Frailty Pathway and the Frailty Team have been accepted onto the EQUIP programme with facilitators to work with the team on measuring outcomes.
Acute Frailty Team

## Slide 11
SDEC Action Plan reviewed and agreed that this be incorporated into a review of the Front Door model at Bronglais General Hospital.
Clinically led Front Door working group to be established.
Workshop to be arranged to review the front door model and related pathways which will include consideration of the model in place at Withybush General Hospital.
Revised Front Door model to be developed and agreed by the end of January 2024.
Planned for implementation February to March 2024.
Front Door Model at Bronglais General Hospital

## Slide 12
  Multidisciplinary Team (MDT) Rooms have been set up for Virtual Consultations and MDT Appointments.
  Final Business Case for Patient Flow and E-Obs system developed and due to be approved by HDdUHB Board in Quarter 4 2023/24. Faculty/Frontier has been implemented which supports business intelligence (AI).
  BECS (Bedside Entertainment and Communications System) pilot commenced at Prince Philip Hospital on 4 wards. Rollout programme not yet agreed.
  Bronglais Strategy Digital Action plan to be refreshed to understand both the acute and intermediate care requirements.
Digital Strategy for Bronglais

## Slide 13
Chemotherapy Day Unit - Services will be relocated from Leri ward as part of the Bronglais General Hospital Chemotherapy Day Unit project due to be completed by 2025. Tenovus Cancer Care mobile support unit to Bronglais Hospital to allow patients to continue to receive their treatment on the site while building works are taking place.
Create patient accommodation at Bronglais General Hospital - Relocation of front of house plant to roof to create patient accommodation explored but not feasible. Post COVID-19 review to be undertaken which will consider looking at available opportunities at Aberystwyth Integrated Care Centre and other sites to release space at Bronglais General Hospital in different ways.
Use of Bronglais General Hospital Estates

## Slide 14
Cancer services
Chemotherapy Day Unit - Vision shared for the new unit, design team progressing on the development design to go out to tender to appoint contractor, with the aim for building work to begin in early 2024.
Radiotherapy and chemotherapy pathways - Mid Wales representation on the South West Wales Cancer Oncology Outpatients and Radiotherapy working groups. Opportunity for the provision of bisphosphonate infusion therapy on an additional community site in Powys.
Palliative Care - National Clinical Lead for the National Palliative and End of Life care programme has asked that the Joint Committee team support the national team in facilitating group discussions on a Mid Wales level which will inform the national programme work.

## Slide 15
Second Colorectal Consultant surgeon commenced in post November 2022.
Newtown Colorectal task and finish group completed its work and produced a report in March 2023 on looking at establishing colorectal clinics, to be provided by HDdUHB, at Newtown as part of care closer to home.
Feasibility report from the HDdUHB Commissioning team identified that it may not be possible to take on additional activity due to the potential impact on the current HDdUHB waiting list.
Colorectal services

## Slide 16
Mid Wales Colorectal services task and finish group established in September 2023.
Purpose of group is to support HDdUHB, PTHB and BCUHB in establishing a sustainable Colorectal services pathway for Mid Wales, which ensures a Mid Wales focus on service delivery and creates opportunities for the provision of outreach services across the Care Hubs in Mid Wales.
Phase 1 - Newtown clinic for PTHB patients (first appointment) Move PTHB work from Bronglais General Hospital back to Newtown, Powys - Target January 2024
First stage to review waiting list and activity data currently in progress.
Colorectal services